## RAID Log
ID | Type | Description | Impact | Owner | Escalation Level | Escalation Date | Status | Resolution
R-01 | Risk | Vendor API delivery delay | High | Scrum Master | Program Manager | 2025-03-14 10:30 | Mitigated | Backlog resequenced, vendor SLA enforced
I-02 | Issue | Build pipeline failure | Medium | Dev Lead | Engineering Manager | 2025-03-18 14:10 | Resolved | Pipeline rollback and hotfix applied
A-03 | Assumption | Stable cloud environment | Medium | Product Owner | None | N/A | Validated | Confirmed with Cloud Ops
D-04 | Dependency | Security review approval | High | Security Team | Director of IT | 2025-03-20 09:00 | Closed | Approval received before sprint end